	Activities
	Institution in charge
	Deliverables

	1
	 Preparation
	Α.1
	Organization of the first partners'meeting  and educator's Seminar

 
	LRF, EA
	Seminar Programme

	2
	
	Α.2
	First Partner's meeting 
	LRF, EA
	Minutes of Meeting

	3
	
	Α.3
	Design of research methodology
	Expert
	

	4
	
	Α.4
	Seminar targeted at educators
	LRF, EA
	

	

	5
	        Implementation
	Β.1
	Composition of research questionnaires
	Expert
	

	6
	
	Β.2
	Interviews
	EA, partner schools
	

	7
	
	Β.3
	Field Research
	EA, partner schools
	

	8
	
	Β.4
	Data Submission to the e-tool
	LRF, EA, partner schools
	

	9
	
	Β.5
	Data processing in class
	EA, partner schools
	

	10
	
	Β.6
	Data Processing in Collaboration with the journalists 
	LRF, partner schools
	

	11
	
	Β.7
	Data Processing in collaboration with the expert.
	LRF, EA, Expert
	

	12
	
	Β.8
	First Draft of the Articles by the students
	EA, partner schools
	

	13
	
	Β.9
	Article editing in collaboration with the journalists
	LRF, partner newspapers
	

	

	14
	           Production 
	C.1
	Production / Reproduction of the evaluation - questionnaires 
	EΑ
	Research questionnaires 

	15
	
	C.2
	Development of the Projects' Implementation Guide
	Expert, ΕΑ, LRF
	

	16
	
	C.3
	Production / Reproduction of the Project's Implementation Guide
	LRF
	Project Implementation Guide

	17
	
	C.4
	Production of the project's Web Site
	EPINOIA,  Creative Marketing
	WEB site 

	18
	
	C.5
	Construction of the e-tool and the Web-based Database
	EPINOIA
	e-tool/Web based database

	19
	
	C.6
	Construction of the  students’ Bulletin Board/mailing list
	EPINOIA
	Students BB 

	20
	
	C.7
	Construction of the educators’ Bulletin Board/mailing list
	EPINOIA
	Educators BB

	21
	
	C.8
	Construction of the Journalists’ Bulletin Board/mailing list
	EPINOIA
	Journalists BB

	22
	
	C.9
	Production / reproduction of the articles (4 issues)
	LRF, partner newspapers
	Student / Journalist Articles (4 issues)

	23
	
	C.10
	Production / reproduction of the project's Handbook
	LRF
	Handbook of the Project (Good Practice Guide)

	           

	24
	             Evaluation
	D.1
	Evaluation Methodology Design 
	Expert
	Evaluation Method

	25
	
	D.2
	Composition of student Questionnaires
	EA
	Student Questionnaires

	26
	
	D.3
	Composition of educator Questionnaires
	EA
	Educator Questionnaires

	27
	
	D.4
	Composition of journalist Questionnaires
	LRF
	Journalist Questionnaires

	28
	
	D.5
	Compilation of data out of student questionnaires
	EA
	

	29
	
	D.6
	Compilation of data out of educator questionnaires
	EA
	

	30
	
	D.7
	Compilation of data out of journalist questionnaires
	LRF
	

	31
	
	D.8
	Statistical data evaluation
	EA, LRF
	

	32
	
	D.9
	Evaluation Report
	EA, LRF
	Project Evaluation Report

	33
	
	D.10
	Compilation of the project's Handbook
	EA, LRF
	

	

	34
	Dissem.


	  E.1
	Presentation in conferences and seminars
	LRF, EA
	Presentations

	35
	
	E.2
	Publications
	LRF, EA
	Publications

	36
	
	E.3
	Press Releases
	LRF, partner newspapers
	Press Releases

	37
	
	E.4
	Posting of the deliverables to interested institutions
	LRF
	

	

	38
	 Management
	F.1
	Project Management
	LRF
	

	39
	
	F.2
	Partner Meetings
	LRF, EA
	Minutes of Meeting

	40
	
	F.3
	Communication
	LRF, EA
	

	41
	
	F.4
	Translation
	EA
	

	42
	
	F.5
	Monthly reports
	LRF
	Monthly Progress Reports

	43
	
	F.6
	Pedagogical Support
	ΕΑ
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